## Sheet1
# | Nav Link | Screen | Device | Issue | Comment | Status | Remark | view
1 | - | Login | all | Login acces without user agree check | Disable login button if agree check is uncheked and disable enter keydown event | open | Done | trustee/investor
2 | - | dashboard | mobile | Login user details are not visible |  | done |  | trustee/investor
3 | - | navbar | all | unresponsive |  | open | Done | trustee/investor
4 | - | user icon letter | web | must be circular div |  | open | working on it | trustee/investor
5 | - | navbar | web | sub-menu options not visibile |  | open | working for about us but not for transaction (Done) | trustee/investor
6 | - | login with phone | all | icon overlapping with input field |  | done |  | trustee/investor
7 | - | change password | all | page not available (nothing happens on click of change password link) |  | open | Done | trustee/investor
8 | contact us | contact us | all | page input field no validation |  | done | This issue is done but nothing happens when click on submit button | trustee/investor
9 | contact us | contact us | web | page font color must be same as login page |  | open | Done | trustee/investor
10 | insights | operational highlights | mobile | page design issue |  | open |  | trustee/investor
11 | insights | Geographical concentration | all | total row font style doesn't match with table rows font-style |  | open | Done | trustee/investor
12 | insights | Product concentration | all | total row font style doesn't match with table rows font-style |  | open | Done | trustee/investor
13 | insights | insigths/collection efficiency | all | same graphs displayed twice |  | open | In pdf, there were 2 graphs. We added entry from admin only. | trustee/investor
14 | insights | net worth | all | capital infusion detail table investor row data should be left align |  | open | Done | trustee/investor
15 | insights | liquidity | all | total row font style doesn't match with table rows font-style |  | open | Done | trustee/investor
16 | insights | strong liability profile | all | no data |  | open | No response yet on what to put | trustee/investor
17 | insights | strong liability profile: well placed | all | no data |  | open | No response yet on what to put | trustee/investor
18 | insights | covid relief | all | total row font style doesn't match with table rows font-style |  | open | Done | trustee/investor
19 | Current Deals | Current Deals | all | filter by name or rating works but when click on sort by it shows all data Filter by deal category is not working |  | open | Done | trustee/investor
20 | Newsletter | newsletter | mobile | filter categories available at the bottom of page had to scroll whole page to access |  | open | Done | trustee/investor
21 | Newsletter | newsletter | all | selected category must be highlighted clear button must not appear on page load it should appear only if there is category selection |  | open | Done | trustee/investor
22 | Newsletter | newsletter | all | news modal should have fixed header and body should have scroll (i.e. news modal window must have fixed height respective to screen size) |  | open | not discussed | trustee/investor
23 | transaction | all forms | all | uploaded documents are not visible |  | open | Done | trustee
24 | transaction | all forms | all | all forms except Assignment not working only loading |  | done |  | trustee
25 | Lender | Lender Document | web | Preview display lable expiry date and edit mode display publish date |  | open | Done | admin